{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketing plan data","List data"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Marketing plan data","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Marketing plan data",null,"STATUS COLOUR LEGEND & TOGGLE"]
[null,"Marketing plan lists"]
[{"$nulls":3},"Not started","In progress","Delayed","Complete","Custom 1","Custom 2","Custom 3","Custom 4"]
[{"$nulls":3},"ON","ON","OFF","ON","OFF","OFF","OFF","OFF"]
[null,"TASK","STATUS","OWNER","ASSIGNED TO","ANTICIPATED\nSTART DATE","ANTICIPATED\nEND DATE","ACTUAL \nSTART DATE ","ACTUAL \nEND DATE ","ESTIMATED COST","ACTUAL COST"]
[null,"Product analysis","In progress","John C.","John C.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":1500,"d":"£1,500"},{"v":1250,"d":"£1,250"}]
[null,"Design storyboards","In progress","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":2000,"d":"£2,000"},{"v":1840,"d":"£1,840"}]
[null,"Review storyboard design","Complete","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":1450,"d":"£1,450"}]
[null,"Research analysis phase I","Delayed","Kamil A.","Andrew L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":3000,"d":"£3,000"},{"v":3200,"d":"£3,200"}]
[null,"Advertising content creation phase I","Delayed","Kamil A.","Timothy S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":500,"d":"£500"}]
[null,"Product requirement definitions","Delayed","Kamil A.","Vivian A.",{"$nulls":4},{"v":575,"d":"£575"},{"v":125,"d":"£125"}]
[null,"Prototype development specifications","In progress","Kamil A.","Gabe F.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":1750,"d":"£1,750"}]
[null,"Quality control, progress reports","In progress","Mark M.","Kamil A.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":925,"d":"£925"},{"v":250,"d":"£250"}]
[null,"Create storyboards","Not started","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":2000,"d":"£2,000"},{"v":1840,"d":"£1,840"}]
[null,"Review storyboards with graphic artists","Delayed","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":1450,"d":"£1,450"}]
[null,"Research analysis phase II","Complete","Kamil A.","Andrew L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":3000,"d":"£3,000"},{"v":3200,"d":"£3,200"}]
[null,"Advertising content creation phase II","Not started","Kamil A.","Timothy S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":500,"d":"£500"}]

{"sheet":"List data","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Marketing plan lists"]
[null,"Marketing plan data"]
[null,"NAME","TITLE"]
[null,"John C.","Marketing Specialist"]
[null,"Mark M.","Marketing Manager"]
[null,"Kamil A.","Project Manager"]
[null,"Phil G.","Marketing Analyst"]
[null,"Andrew L.","Research Coordinator"]
[null,"Timothy S.","Marketing Specialist"]
[null,"Vivian A.","Marketing Analyst"]
[null,"Gabe F.","Associate Marketing Manager"]