## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2023-08-14 | 2023-10-13 | 210 | 59 | 2023-08-14 | 2023-10-18 | 300 | 64
Project 2 | Category 2 | Employee 4 | 2023-09-07 | 2023-10-08 | 400 | 31 | 2023-09-07 | 2023-10-11 | 390 | 34
Project 3 | Category 1 | Employee 2 | 2023-07-10 | 2023-09-08 | 500 | 58 | 2023-07-10 | 2023-09-21 | 500 | 71
Project 4 | Category 2 | Employee 3 | 2023-07-20 | 2023-07-30 | 250 | 10 | 2023-07-20 | 2023-08-08 | 276 | 18
Project 5 | Category 3 | Employee 2 | 2023-07-20 | 2023-08-29 | 300 | 39 | 2023-07-20 | 2023-09-04 | 310 | 44
Project 6 | Category 4 | Employee 4 | 2023-08-19 | 2023-08-29 | 500 | 10 | 2023-08-19 | 2023-09-03 | 510 | 14
Project 7 | Category 5 | Employee 1 | 2023-09-04 | 2023-09-28 | 750 | 24 | 2023-09-04 | 2023-10-03 | 790 | 29
Project 8 | Category 2 | Employee 1 | 2023-09-09 | 2023-10-18 | 450 | 39 | 2023-09-03 | 2023-10-13 | 430 | 40
Project 9 | Category 4 | Employee 1 | 2023-07-15 | 2023-08-04 | 250 | 19 | 2023-07-20 | 2023-07-30 | 200 | 10
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS