{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Données du plan marketing","Données de liste"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Données du plan marketing","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"merged":[[0,3,0,10],[1,1,3,1],[1,3,1,10]]}
[null,"Données du Plan Marketing"]
[null,"Listes du Plan Marketing",null,"Légende et bouton des couleurs d’état"]
[{"$nulls":3},"Non commencé","En cours","Retardé","Terminé","Personnalisé 1","Personnalisé 2","Personnalisé 3","Personnalisé 4"]
[{"$nulls":3},"ACTIVÉ","ACTIVÉ","ACTIVÉ","ACTIVÉ","ACTIVÉ","ACTIVÉ","ACTIVÉ","ACTIVÉ"]
[]
[null,"Tâche","Statut","Propriétaire","Attribué à","Date de fin\nDate de début","Prévu\nDate de fin","Réel\nDate de début","Réel\nDate de fin","Coût estimé","Réel Coût"]
[null,"Analyse produit","Non commencé","Alexandre C.","Alexandre C.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},null,{"v":1500,"d":"1,500 €"},{"v":1250,"d":"1,250 €"}]
[null,"Conception des storyboards","En cours","Maurice B.","Alexandre C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"2,000 €"},{"v":1840,"d":"1,840 €"}]
[null,"Examen de la conception des storyboards","Retardé","Maurice B.","Alexandre C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"1,450 €"}]
[null,"Étude et analyse (phase 1)","Terminé","David B.","Noël B.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"3,000 €"},{"v":3200,"d":"3,200 €"}]
[null,"Création de contenu publicitaire (phase 1)","Personnalisé 1","David B.","Jérôme R.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"500 €"}]
[null,"Définition des exigences du produit","Personnalisé 2","Jérôme R.","Marie B.",{"$nulls":4},{"v":575,"d":"575 €"},{"v":125,"d":"125 €"}]
[null,"Spécifications du développement de prototype","Personnalisé 3","David B.","Sébastien C.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2019-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2019-09-25"},null,null,{"v":1750,"d":"1,750 €"}]
[null,"Contrôle qualité, rapports d’avancement","Personnalisé 4","Maurice B.","David B.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2019-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},null,{"v":925,"d":"925 €"},{"v":250,"d":"250 €"}]
[null,"Création des storyboards","Non commencé","Maurice B.","Alexandre C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"2,000 €"},{"v":1840,"d":"1,840 €"}]
[null,"Examen des storyboards avec les graphistes","Retardé","Maurice B.","Alexandre C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"1,450 €"}]
[null,"Étude et analyse (phase 2)","Terminé","David B.","Noël B.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"3,000 €"},{"v":3200,"d":"3,200 €"}]
[null,"Création de contenu publicitaire Phase II","Non commencé","David B.","Jérôme R.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"500 €"}]

{"sheet":"Données de liste","index":1,"n_rows":12,"n_cols":3,"rows_kept":12,"merged":[[0,1,0,2],[1,1,1,2]]}
[null,"Listes du Plan Marketing"]
[null,"Données du Plan Marketing"]
[]
[null,"Nom","Titre"]
[null,"Alexandre C.","Spécialiste marketing"]
[null,"Maurice B.","Responsable marketing"]
[null,"David B.","Responsable de projet"]
[null,"Alain L.","Analyste marketing"]
[null,"Noël B.","Coordinateur de recherche"]
[null,"Jérôme R.","Spécialiste marketing"]
[null,"Marie B.","Analyste marketing"]
[null,"Sébastien C.","Responsable marketing associé"]