{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketingterv adatai","Listaadatok"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Marketingterv adatai","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Marketingterv adatai",null,"ÁLLAPOT SZÍNÉNEK JELMAGYARÁZATA ÉS KAPCSOLÓJA"]
[null,"Marketingterv listák"]
[{"$nulls":3},"Kezdésre vár","Folyamatban","Késik","Kész","Egyéni 1","Egyéni 2","Egyéni 3","Egyéni 4"]
[{"$nulls":3},"BE","BE","KI","BE","KI","KI","KI","KI"]
[null,"FELADAT","ÁLLAPOT","TULAJDONOS","FELELŐS","VÁRHATÓ\nKEZDÉSI \nDÁTUM","VÁRHATÓ\nBEFEJEZŐ DÁTUM","TÉNYLEGES \nKEZDÉSI\nDÁTUM ","TÉNYLEGES \nBEFEJEZŐ DÁTUM ","BECSÜLT KÖLTSÉG","TÉNYLEGES \nKÖLTSÉG"]
[null,"Termékelemzés","Folyamatban","B. Endre","B. Endre",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":300000,"d":"300,000 Ft"},{"v":250000,"d":"250,000 Ft"}]
[null,"Forgatókönyvterv készítése","Folyamatban","K. Kevin","B. Endre",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":400000,"d":"400,000 Ft"},{"v":368000,"d":"368,000 Ft"}]
[null,"Forgatókönyvterv elemzése","Kész","K. Kevin","B. Endre",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":290000,"d":"290,000 Ft"}]
[null,"Kutatási elemzés – 1. fázis","Késik","V. Rozália","B. András",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":600000,"d":"600,000 Ft"},{"v":640000,"d":"640,000 Ft"}]
[null,"Tartalomlétrehozási hirdetés – 1. fázis","Késik","V. Rozália","P. Tivadar",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":100000,"d":"100,000 Ft"}]
[null,"Termékkövetelmények meghatározása","Késik","V. Rozália","Gy. Izabella",{"$nulls":4},{"v":115000,"d":"115,000 Ft"},{"v":25000,"d":"25,000 Ft"}]
[null,"Prototípus fejlesztésének jellemzői","Folyamatban","V. Rozália","N. Géza",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":350000,"d":"350,000 Ft"}]
[null,"Minőség-ellenőrzés, haladási jelentések","Folyamatban","K. Kevin","V. Rozália",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":185000,"d":"185,000 Ft"},{"v":50000,"d":"50,000 Ft"}]
[null,"Forgatókönyv készítése","Kezdésre vár","K. Kevin","B. Endre",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":400000,"d":"400,000 Ft"},{"v":368000,"d":"368,000 Ft"}]
[null,"Forgatókönyv áttekintése grafikusokkal","Késik","K. Kevin","B. Endre",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":290000,"d":"290,000 Ft"}]
[null,"Kutatási elemzés – 2. fázis","Kész","V. Rozália","B. András",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":600000,"d":"600,000 Ft"},{"v":640000,"d":"640,000 Ft"}]
[null,"Tartalomlétrehozási hirdetés – 2. fázis","Kezdésre vár","V. Rozália","P. Tivadar",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":100000,"d":"100,000 Ft"}]

{"sheet":"Listaadatok","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Marketingterv listák"]
[null,"Marketingterv adatai"]
[null,"NÉV","BEOSZTÁS"]
[null,"B. Endre","Marketing specialista"]
[null,"K. Kevin","Marketing menedzser"]
[null,"V. Rozália","Projektmenedzser"]
[null,"D. Gábor","Marketingelemző"]
[null,"B. András","Kutatási koordinátor"]
[null,"P. Tivadar","Marketing specialista"]
[null,"Gy. Izabella","Marketingelemző"]
[null,"N. Géza","Helyettes marketing menedzser"]